## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 87 | 0 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-04-03 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02 | 2017-04-03 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | GamePlay | [23 empty] | Assigned
6 | 1 | Pivot to Action Game | ALL |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 5 | 3 | 2 | 2 | 0 | 0 | 0 | 0 |  | Active
7 | 2 | Trucks to Carry Items | MS | DV | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 0 | 0 |  | Verify?
8 | 3 | Add Point Values for Items | MS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 |  | Fixed
9 | 3 | Add Weight Values for Items | MS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 |  | Deferred
10 | 2 | 4 Player Camera | DV |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 1 | Set Up New Level Objects | KG | DV | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 2 | Co-Op Scoring | MS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2 | Truck Capacity and Co-Op Elements | MS | DV | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 0 | 0
14 | 3 | Space Out Items in Truck | DV |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
15 | 3 | Misc Co-Op Elements | MS |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0
16 | 2 | Block Off Items When Capacity is Reached | DV | MS | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0
17 | 3 | Music Implementation | AT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0
18 | 2 | Update Camera Function on Stairs | DV | MS | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
19 |  | Aesthetics
20 | 1 | New Updated Level | AT |  | 6 | 0 |  |  | 6 | 6 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3 | Updated Characters | AT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
22 | 2 | Truck Art | AT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
23 | 1 | Team UI | KG | DV | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
24 | 1 | Clock UI | MS | DV | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0
25 | 1 | Pickup Prompt | DV |  | 3 | 0 |  |  | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0
26 | 2 | Start Screen | DV |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
27 | 3 | Controller Select Menu | DV |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
28
29
30 |  | Misc
31 | 1 | Controller Select | DV | MS | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 3 | 3 | 3 | 0 | 0 | 0
32 | 1 | Justification Document | KG | ALL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
33 | 1 | Pivot Playtest Document | KG | ALL | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
34 | 1 | Burndown Chart | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
35 | 2 | Video Tutorial | KG |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 0 | 0
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 87 | 87 | 80.7857 | 74.5714 | 68.3571 | 62.1429 | 55.9286 | 49.7143 | 43.5 | 37.2857 | 31.0714 | 24.8571 | 18.6429 | 12.4286 | 6.2143 | 0
212
213 |  | Sum | [6 empty] | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 40 | 40 | 40 | 37 | 37 | 35 | 32 | 23 | 23 | 15 | 15 | 13 | 11 | 5 | 0 | 0
216 |  |  | 2 | [5 empty] | 28 | 28 | 28 | 28 | 28 | 28 | 25 | 24 | 24 | 24 | 20 | 16 | 11.5 | 9.5 | 0 | 0
217 |  |  | 3 | [5 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 18 | 18 | 17 | 9 | 5 | 4 | 2 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Alex Turner | AT |  |  |  |  | AT | 14 | 14 | 14 | 12 | 12 | 11 | 11 | 10 | 10 | 7 | 6 | 1 | 1 | 0 | 0 | 0
223 |  | Kari Green | KG |  |  |  |  | KG | 16 | 16 | 16 | 16 | 16 | 15 | 14 | 12 | 12 | 10 | 10 | 8 | 6.5 | 5.5 | 0 | 0
224 |  | Dave Vader | DV |  |  |  |  | DV | 24 | 24 | 24 | 23 | 23 | 23 | 21 | 17 | 17 | 15 | 12 | 11 | 9 | 4 | 0 | 0
225 |  | Michael Scheible | MS |  |  |  |  | MS | 22 | 22 | 22 | 22 | 22 | 22 | 21 | 19 | 19 | 19 | 12 | 10 | 9 | 6 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 7 | 7 | 5 | 4 | 4 | 1 | 1 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87
236

## Daily Scrum
Producer | 2017-04-03 |  | Team Members
Approved | Dates |  | Alex Turner | Kari Green | Dave Vader | Michael Scheible | All
| 2017-03-20 | Mon |  |  |  |  | Turn in Alpha
| 2017-03-21 | Tue
| 2017-03-22 | Wed |  |  |  |  | Group Meeting at The Union
| 2017-03-23 | Thu |  |  | 482 Project can't meet |  | Remove Guards From Game
| 2017-03-24 | Fri | Think of How we make challenging without guards | Tutorial |  | Think of a good way to Give Intro of 4 Characters | Meet With Mitchell
| 2017-03-25 | Sat | Needs to Draw New Level | Implement GameObjs for New Level | In Charge of Team Select and Scaling back Abilities | Focus on Implementing and coming up with Co-op Elements | Pivot to 2v2 Game
| 2017-03-26 | Sun |  |  |  | Can't Meet 441 Stuff
| 2017-03-27 | Mon
| 2017-03-28 | Tue |  |  | Made a Start Menu
| 2017-03-29 | Wed | Make Background Music |  |  | Add Trucks to Carry Loot
| 2017-03-30 | Thu |  | Making Tutorial a Video Now
| 2017-03-31 | Fri |  |  |  |  | Meet With Mitchell
| 2017-04-01 | Sat |  | Email Music Partner for Sound when adding items to the truck | Fix Item Allignment in Truck |  | Group Meeting at The Union
| 2017-04-02 | Sun |  |  |  | Fix Team Selection Problem, Update Item Points and Weight
| 2017-04-03 | Mon
| 2017-04-04 | Tue
| 2017-04-05 | Wed
| 2017-04-06 | Thu
| 2017-04-07 | Fri
| 2017-04-08 | Sat
| 2017-04-09 | Sun
| 2017-04-10 | Mon