## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 245.42 | 159.92 |  |  |  | 19 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 3/06 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-02-15 | 2/17 | 2/18 | 2/19 | 2/20 | 2/22 | 2/24 | 2/25 | 2/26 | 2/27 | 3/01 | 3/03 | 3/04 | 3/05 | 3/06 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 |  | ALL |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Assigned
6 | 2 |  | ALL |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
8 | [25 empty] | Fixed
Make Characters | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
10 | 1 | Game Controller Input | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 |  | Player Model | [23 empty] | Can't Repro
12 | 1 | Player Movement (Single Level) | DV |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Player Movement (Vaulting + Multiple Levels)
14 | 1 | Pickup + Putdown Objects | DV |  | 2 | 0.5 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
15 |  | Player Object Aiming (for aimable objects)
58 | 1 | Knock-out | MS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
68 | 1 | Revive Someone | MS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
69 | 1 | Be Revived | MS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
70 | 1 | Be Inside an Object (closet, box) | DV |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 1 | Pickup Highlight in Red with message | KG | DV | 3 | 1 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1
72
73
74
75
16
Make Objects
18 | 1 | Magical Key | DV |  | 1 | 1 |  |  | 1 | bar: Wed to Mon
19 |  | Magical Rope
20 | 1 | Magical Nightstick | MS |  | 2 | 1.5 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5
21 | 1 | Magical Box | DV |  | 3 | 0 |  |  | 3 | 3 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1 | Lamp Object | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
23 |  | Taser Object
24 | 1 | Tree Plant | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
25 |  | Ficus Plant
26 |  | Fern Plant
27 |  | Bonzai Plant
28 |  | Step Ladder Object
29 |  | Chair Object
30 |  | Banana Peel Object
31 |  | Frying Pan Object
32 |  | Umbrella Object
33 |  | Coat Rack Object
34 | 1 | Radio Object | DV |  | 2 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
35 |  | Book Object
36 | 1 | Mug Object | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
37 |  | Alcohol Object
38 | 1 | Flashlight Object | ALT |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | Gun Object
40 | 1 | Loot Object | KG | MS | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | 0 | 0
41 |  | Coffee Pot Object
42
43
Object Mechanics
45 | 1 | Open Door Ability | ALT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
46 |  | Rope Ability
47 | 1 | Plant Ability | KG |  | 1 | 1 |  |  | 1 | bar: Wed to Mon
48 | 1 | Hide Ability | DV |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | Light Ability | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  | Distant Knockout Ability
51 |  | Climb Ability
52 |  | Sit Ability
53 |  | Slip Ability
54 | 1 | Placeable Ability | MS |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
55 | 1 | Distract Ability | DV |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
56 |  | Relax Ability
57 |  | Drunk Ability
59 |  | Permanent Knockout Ability
60
61
62
63
64
65
66
67
76
Level Mechanics
78 |  | Sun Setting Mechanics
79 |  | Window Mechanic
80 |  | Elevator Mechanics
81 | 1 | Closet Mechanic | DV |  | 2.5 | 0 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 1 | Door Mechanic | ALT |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
83 | 1 | Alarm Mechanic | MS |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
84 |  | Gunpoint-Style CCTV Cameras
85 | 1 | Digital Timer | MS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
86
87
Camera Mechanics
89 | 1 | Always Keep Players in View (max range) | ALT |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90 |  | Visited Portions Have Blueprint When not in view
91 | 2 | In View But No Light = Outline | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 2 | In View With Light = Light Beam | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 2 | Light Mechanic with Doors | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
94 |  | Door Peek Mechanic
95
96
97
98
99
Enemies
101 | 1 | Enemy Object | ALT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 1 | Guards Object | ALT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  | Police Object
104 |  | CCTV Object
105
Enemy Mechanics | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 1 | Use Flashlight (aim) | MS |  | 1 | 0.25 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 0.25 |  | Reported
108 |  | CCTV Camera Rotate | [23 empty] | Reported
109 | 1 | Suspicion Triggers | MS |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
110 | 1 | Raise Alarm | MS |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
111 | 1 | Patrol | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
112 | 1 | Search | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
113 |  | Shoot Mechanic | [23 empty] | Reported
114 |  | Relax Mechanic | [23 empty] | Reported
115 | [25 empty] | Reported
GUI Mechanics | [25 empty] | Reported
117 | 1 | Circular Progress Bars | DV |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
118 | 1 | Castle Crashers Like Player Icons | DV |  | 1 | 0.25 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | Reported
119 | 1 | Player Status Indicator | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
120 | 1 | In-Game Character Status Indication (Suspicious, Drunk, Alarmed, Knocked out) | DV |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
121 | 1 | Current Object Holding Indicator | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
Main Menu | [25 empty] | Reported
127 |  | Title Logo | [23 empty] | Reported
128 |  | Level Selector | [23 empty] | Reported
129 |  | Character Selector | [23 empty] | Reported
130 | [25 empty] | Reported
Win Screen | [25 empty] | Reported
132 |  | Points Indicator | [23 empty] | Reported
133 | 1 | Time Indicator | MS |  | 1 | 0.5 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 |  | Reported
134 |  | Point Breakdown | [23 empty] | Reported
135 |  | Statistics about the game | [23 empty] | Reported
136 | [25 empty] | Reported
Lose Screen | [25 empty] | Reported
138 | 1 | Restart Button | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
139 | 1 | Quit Button | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
140 | [25 empty] | Reported
Puzzle Mechanics | [25 empty] | Reported
142 | 1 | Button Trigger | MS |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
143 |  | Lasers | [23 empty] | Reported
144 |  | Timed Button | [23 empty] | Reported
145 | [25 empty] | Reported
Level Design | [25 empty] | Reported
147 | 1 | Floor | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
148 | 1 | Walls | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
149 | 1 | Doors | ALT |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Reported
150 |  | Stairs | [23 empty] | Reported
151 |  | Breakable Windows | [23 empty] | Reported
152 | 1 | Windows | MS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Reported
153 | 1 | Ceilings | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
154 | 1 | Lighting | ALT |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
155 | 1 | Global Backdrop | KG |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
156 | 1 | Tables | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
157 |  | Bookshelves | [23 empty] | Reported
158 |  | Kitchen | [23 empty] | Reported
159 |  | Office | [23 empty] | Reported
160 | 1 | Vault | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
161 | 1 | Lobby | MS |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
162 |  | Walkways | [23 empty] | Reported
163 |  | Escalators | [23 empty] | Reported
164 | 1 | Level Overview Cam + Button To Start | KG |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | Reported
165 | 1 | Navigation Routes | ALT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
166 | 1 | Puzzles | MS | KG | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | Reported
167 |  | Catwalks | [23 empty] | Reported
168 | 1 | Closet Positioning | KG |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: Wed to Mon
169 | 1 | Room Backdrop | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
170 |  | Pictures | [23 empty] | Reported
171 |  | Office Supplies | [23 empty] | Reported
172 |  | Funny Motivational Posters | [23 empty] | Reported
173 |  | Computers | [23 empty] | Reported
174 |  | Demotivational Posters | [23 empty] | Reported
175 |  | Room Numbers | [23 empty] | Reported
176 | 420 | 420 Room Number + Plant | MS |  | 0.42 | 0.42 |  |  | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 |  | Reported
177 |  | Ground Types (Carpet, Concrete, Tile, Glass) | [23 empty] | Reported
178 |  | Ceiling Types (Glass, Solid) | [23 empty] | Reported
179 |  | Functional Windows (Shades, Shades Retracted, Open) | [23 empty] | Reported
180 |  | Cabinets | [23 empty] | Reported
181 |  | Functional Cabinets | [23 empty] | Reported
182 |  | Vending Machines | [23 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
Background Sprites | [25 empty] | Reported
186 | 1 | Cityscape Layers | KG |  | 10 | 5 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 |  | Reported
187 | 3 | Water Cooler | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
188 | 3 | Sink | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
189 | 3 | Fridge | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
190 | 3 | Conference Room Chairs | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
191 | 3 | Conference Room Table | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
192 | 3 | Cabinets | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
193 | 3 | Tables | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
194 | 3 | Front Desk | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
195 | 3 | Computers | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
196 | 2 | Briefcases | KG |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 |  | Reported
197 | 3 | Hanging Lights | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
198 | 3 | Door Keypad | KG |  | 1.5 | 1.5 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | Reported
199 | 2 | Door | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
200 | 3 | Main Buildings | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
201 | 3 | Skywalk | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
202 | 3 | Railing | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
203 | 2 | Escalator | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
204 | 2 | Elevator | KG |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Reported
205 | 3 | Other Misc Background Sprites for Buildings | KG |  | 60 | 60 |  |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 |  | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 19 | 19 | 17 | 16 | 15 | 14 | 12 | 10 | 9 | 8 | 7 | 5 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 245.42 | 245.42 | 219.6 | 206.7 | 193.8 | 180.8 | 155.0 | 129.2 | 116.3 | 103.3 | 90.4 | 64.6 | 38.8 | 25.8 | 12.9 | 0.0
212
213 |  | Sum | [6 empty] | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 120.5 | 120.5 | 120.5 | 119 | 112.5 | 105 | 105 | 96 | 84 | 79 | 66.25 | 52.75 | 52.75 | 51.25 | 50 | 50
216 |  |  | 2 | [5 empty] | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 9 | 9 | 9 | 9 | 9
217 |  |  | 3 | [5 empty] | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5 | 100.5
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Michael Scheible | MS |  |  |  |  | MS | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 26.42 | 24.42 | 21.42 | 21.42 | 19.92 | 18.67 | 18.67
223 |  | Dave Vader | DV |  |  |  |  | DV | 27.5 | 27.5 | 27.5 | 26 | 19.5 | 12 | 12 | 12 | 12 | 12 | 6.75 | 6.75 | 6.75 | 6.75 | 6.75 | 6.75
224 |  | Kari Green | KG |  |  |  |  | KG | 146.5 | 146.5 | 146.5 | 146.5 | 146.5 | 146.5 | 146.5 | 146.5 | 144.5 | 144.5 | 142.5 | 134.5 | 134.5 | 134.5 | 134.5 | 134.5
225 |  | Alex Turner | ALT |  |  |  |  | ALT | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 28 | 18 | 13 | 9.5 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42 | 245.42
236

## Daily Scrum
Producer | 3/06 |  | Team Members
Approved | Dates |  | Michael Scheible | Dave Vader | Kari Green | Alex Turner | All
| 2/15 | Wed |  |  |  |  | Formed Group, Set meeting date for Sunday
| 2/16 | Thu
| 2/17 | Fri
| 2/18 | Sat
| 2/19 | Sun |  |  |  |  | Discussed basics of game, picked games for R&D, Set up Git
| 2/20 | Mon | Can't start stuff until Friday due to 441 | Player Movement and Controller Input | Wrote R&A Part | Lighting
| 2/21 | Tue |  |  |  | R&A Part Written
| 2/22 | Wed |  | R&A Part Done, Controller Input Done
| 2/23 | Thu |  | Player movement done
| 2/24 | Fri | Wrote R&A Portion, Flying Out to CA |  | Started Player Pickup, Flying out to CA | Lighting Finished, moved onto guard movement
| 2/25 | Sat | Need Help with Git | Joined Kari to help with Player pickup
| 2/26 | Sun | Timer Implemented | Pickup Mostly Done | Player Pickup Mostly Done | Guard and Lamp Stuff Done, assisting other members
| 2/27 | Mon |  | Working with Kari on Closets | Closets with Dave
| 2/28 | Tue |  |  | Started Working on Art assests
| 3/01 | Wed | Knockout and Revive abilities are done -still need to finish alarm and suspicion
| 3/02 | Thu | Birthday
| 3/03 | Fri | Flashlight aiming mostly done still need item object implemented, put in a basic window script |  |  | Out of Town unable to assist until Monday
| 3/04 | Sat | Discussed Demo level with Dave | Discussed Demo level with Mike
| 3/05 | Sun | Started Demo Level Implementatio, Flying Backn | Clean up Demo level, Flying Back | Clean up Demo Level, Flying Back | Clean Up Demo Level
| 3/06 | Mon
| 3/07 | Tue
| 3/08 | Wed