## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 151.5 | 11 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 3/20 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-06 | 3/07 | 3/08 | 3/09 | 3/10 | 3/11 | 3/12 | 3/13 | 3/14 | 3/15 | 3/16 | 3/17 | 3/18 | 3/19 | 3/20 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | AI | [23 empty] | Assigned
6 | 1 | State Machine Backbone | MS |  | 5 | 0 |  |  | 5 | 4 | 5 | 4 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Patrol State | MS |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Search State | MS |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Attack State | MS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 2 | Movement | MS |  | 2.5 | 0 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | NavMesh Didn't work For Gold Spike ; ; | Fact of Life
11 | 2 | Player Interactions | DV | MS | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 |  | Can't Repro
12 | 2 | Field of View Implementation | AT | MS | 2 | 0 |  |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | Colliders | MS | AT | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
14 | 3 | Animation | DV |  | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | Started as Player Animation But Decided to Use for Guard Instead
15 | 4 | Bux Fixes | MS |  | 3 | 1 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1
16 | 5 | KO State | MS |  | 4 | 2.5 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | Not Needed for Alpha But Needed for Beta
17 | 5 | Sit State | MS |  | 4 | 2.5 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | Not Needed for Alpha But Needed for Beta
18
19 |  | Player
20 | 1 | Box Player | DV |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 6 | 5 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Key Player | DV |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0
22 | 1 | Item Interactions | DV |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
23 | 1 | Elevator | DV |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
24 | 2 | Escalator | DV |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Removed From Game
25 | 2 | Flashlight | DV | AT | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
26 | 3 | Opening Doors | DV | MS | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0
27 | 3 | Animations | DV | MS | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | Had to Reanimate Sillouette Style Player
28 | 5 | Gold Bars | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
29 | 3 | Briefcase | DV | KG | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
30 | 4 | Keycard | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
31
32
33 |  | Level Design
34 |  | Design Level in Unity (including all items imported and colliders placed) | KG |  | 30 | 0 |  |  | 30 | 30 | 27 | 24 | 24 | 20 | 16 | 15 | 15 | 12 | 8 | 4 | 4 | 4 | 0 | 0
35 |  | NavMesh | KG | MS | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
36
37 |  | Misc
38 |  | Fine Tuning For Turn Ins | DV | MS | 10 | 0 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | YAY FOR STAYING UP TIL 5AM THE DAY OF TURN IN
39 |  | GITHUB | ALL |  | 20 | 0 |  |  | 20 | 20 | 20 | 20 | 15 | 15 | 15 | 10 | 10 | 10 | 8 | 8 | 6 | 3 | 3 | 0 | GITHUB IS THE DEVIL FOR UNITY
40 |  | Turn In | ALL |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | DO NOT TURN IN SHEEBS' P2 AGAIN
41
42 |  | Artwork
44 | 1 | Cityscape Layers | AT |  | 10 | 5 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
46 | 3 | Sink | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
47 | 3 | Fridge | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3 | Conference Room Chairs | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
49 | 3 | Conference Room Table | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
50 | 3 | Cabinets | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
51 | 3 | Tables | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
52 | 3 | Front Desk | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
53 | 3 | Computers | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
54 | 2 | Briefcases | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
55 | 3 | Hanging Lights | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
57 | 2 | Door | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
58 | 3 | Main Buildings | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
59 | 3 | Skywalk | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
62 | 2 | Elevator | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
63 | 3 | Computers | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
64 | 3 | Couch | AT |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
65 | 4 | Sunset Versions of Normal Objects | AT |  | 12 | 0 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0
66 | 5 | Outline Versions of Normal Objects | AT |  | 12 | 0 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 151.5 | 151.5 | 140.7 | 129.9 | 119.0 | 108.2 | 97.4 | 86.6 | 75.8 | 64.9 | 54.1 | 43.3 | 32.5 | 21.6 | 10.8 | 0.0
212
213 |  | Sum | [6 empty] | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5 | 150.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 41 | 40 | 41 | 40 | 39 | 33 | 25.5 | 22 | 21 | 16 | 13 | 11 | 9 | 5 | 5 | 5
216 |  |  | 2 | [5 empty] | 19.5 | 19.5 | 19.5 | 18.5 | 18.5 | 18.5 | 16.5 | 14.5 | 14.5 | 14.5 | 12 | 12 | 5 | 5 | 0 | 0
217 |  |  | 3 | [5 empty] | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 52 | 52 | 50 | 35.5 | 21.5 | 11.5 | 7 | 0 | 0
218 |  |  | 4 | [5 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 14 | 1 | 1
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 21 | 21 | 21 | 21 | 21 | 21 | 18.5 | 18 | 18 | 18 | 18 | 18 | 18 | 17 | 5 | 5
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Alex Turner | AT |  |  |  |  | AT | 84 | 84 | 84 | 83 | 83 | 83 | 83 | 82 | 82 | 77 | 65 | 53 | 38 | 38 | 5 | 5
223 |  | Kari Green | KG |  |  |  |  | KG | 36 | 36 | 33 | 30 | 30 | 23 | 19 | 20 | 20 | 17 | 13 | 4 | 4 | 4 | 0 | 0
224 |  | Dave Vader | DV |  |  |  |  | DV | 50 | 50 | 50 | 50 | 48 | 45 | 42 | 39 | 33 | 31 | 25.5 | 21.5 | 17.5 | 7 | 5 | 0
225 |  | Michael Scheible | MS |  |  |  |  | MS | 27.5 | 26.5 | 27.5 | 26.5 | 27.5 | 24.5 | 15.5 | 11.5 | 11.5 | 11.5 | 9 | 8 | 8 | 8 | 6 | 6
226 |  | All | ALL |  |  |  |  | ALL | 24 | 24 | 24 | 24 | 19 | 19 | 19 | 14 | 12 | 12 | 10 | 10 | 8 | 5 | 5 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5
236

## Daily Scrum
Producer | 3/20 |  | Team Members
Approved | Dates |  | Alex Turner | Kari Green | Dave Vader | Michael Scheible | All
| 3/06 | Mon |  |  |  |  | Talked About Roles Going Forward
| 3/07 | Tue | Became in Charge of Artwork | Became in Charge of Level Implementation | Became in Charge of Player Interactions | Became In Charge of AI
| 3/08 | Wed |  |  | Started Working on Animations |  | Decided to Meet Up at Shammy Jam
| 3/09 | Thu |  |  |  | Have StateMachine Done By Sat Night
| 3/10 | Fri
| 3/11 | Sat | Artwork Planning: Level | Backbone of Level Done | Basic Animation Done | Statemachine Working in Demo AI Scene | Met at Shammy Jam to Discuss Progress and Future Direction
| 3/12 | Sun | Artwork Planning: Objects | Work on importing items and colliders | Throw Together most of Gold Spike | Throw Together Gold Spike Since Nav Mesh wasn't working
| 3/13 | Mon | Artwork Digitizing
| 3/14 | Tue | Artwork Digitizing |  | Box Player Animations and Scripts Done | Go See Kurt about Nav Mesh
| 3/15 | Wed | Artwork Digitizing | Navmesh is Ok Now, Need to Merge with Artwork
| 3/16 | Thu | Artwork Digitizing
| 3/17 | Fri | Artwork Digitizing |  | Rope Animations Started |  | ST PADDYS
| 3/18 | Sat | Artwork Digitizing | Familial Obligations Can't Meet |  | Finishing Touches on Rope Animations | Dave and Mike Meet at Dude to talk about Getting Everything Together
| 3/19 | Sun | Finishing Touches on Artwork Color Scheme | Finish with items; Justification and Bug Testing | Fixing Together Stuff for Turn In | Figure Out All Layers and Tags | Meet at Dude to Discuss Progress and Future Direction
| 3/20 | Mon
| 3/21 | Tue
| 3/22 | Wed
| 3/23 | Thu
| 3/24 | Fri
| 3/25 | Sat
| 3/26 | Sun
| 3/27 | Mon