## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 68 | 0 |  |  |  | 17 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2
| 2017-04-21 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Thu | Fri | Sat | Sun | Mon | Tue | Thu | Fri | Sat | Sun | Mon | Tue | Thu | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-04-03 | 2017-04-04 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-20 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Trailer | AT |  | 10 | 0 |  |  | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 |  | Assigned
6 | 1 | Tutorial | DV | MS | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 0 |  | Active
7 | 2 | Character Selection Screen | DV | KG | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | Verify?
8 | 1 | Voice Over Effects | KG | DV | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | Fixed
9 | 3 | Design Expo | MS | DV | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 3 | A2GD Expo | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  | Fact of Life
11 | 2 | Game End Fixes | MS | DV | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Can't Repro
12 | 4 | Sunset Background Transition | AT |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
13 | 4 | Coundown to Begin Game | DV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Combat System | DV | MS | 10 | 0 |  |  | 10 | 10 | 8 | 8 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3 | Bleed Effect (For Health Purposes) | KG | DV | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Blue Blood (aka Water for Kid Expo)
16 | 2 | Real Time Events | MS | KG | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 5 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0
17 | 1 | Balancing | KG | ALL | 5 | 0 |  |  | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
18 | 1 | Bugfixing | ALL |  | 6 | 0 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 0
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 17 | 17 | 16 | 14 | 13 | 12 | 11 | 10 | 9 | 7 | 6 | 5 | 4 | 3 | 2 | 0
211 |  | Optimum | [5 empty] | Line | 68 | 68 | 64 | 56 | 52 | 48 | 44 | 40 | 36 | 28 | 24 | 20 | 16 | 12 | 8 | 0
212
213 |  | Sum | [6 empty] | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 40 | 40 | 38 | 38 | 35 | 33 | 26 | 26 | 24 | 24 | 19 | 17 | 5 | 3 | 3 | 0
216 |  |  | 2 | [5 empty] | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 11 | 10 | 7 | 5 | 5 | 2 | 2 | 0 | 0
217 |  |  | 3 | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 5 | 5 | 3 | 3 | 3 | 3 | 0
218 |  |  | 4 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Alex Turner | AT |  |  |  |  | AT | 12 | 12 | 12 | 12 | 12 | 10 | 8 | 8 | 6 | 6 | 6 | 4 | 4 | 0 | 0 | 0
223 |  | Kari Green | KG |  |  |  |  | KG | 12 | 12 | 12 | 12 | 11 | 11 | 9 | 8 | 7 | 8 | 8 | 6 | 0 | 0 | 0 | 0
224 |  | Dave Vader | DV |  |  |  |  | DV | 20 | 20 | 18 | 18 | 16 | 16 | 13 | 12 | 11 | 10 | 7 | 7 | 2 | 2 | 1 | 0
225 |  | Michael Scheible | MS |  |  |  |  | MS | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 12 | 11 | 5 | 3 | 3 | 1 | 1 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 5 | 5 | 5 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68
236

## Daily Scrum
Producer | 2017-04-21 |  | Team Members
Approved | Dates |  | Alex Turner | Kari Green | Dave Vader | Michael Scheible | All
| 2017-04-03 | Mon
| 2017-04-04 | Tue |  |  |  | Sword Combat
| 2017-04-05 | Wed |  |  | Juicy Lights | Added Juice To a Bunch of Items
| 2017-04-06 | Thu |  |  | Update Sword Sprites, RIP Mr Hankey |  | Go Play VR Game
| 2017-04-07 | Fri |  | QA Testing | Gunsssssz | Added Real Time Events
| 2017-04-08 | Sat | Gather Footage For Trailer | Gather Footage for Trailer | 482 Stuff =( | Gather Footage for Trailer
| 2017-04-09 | Sun |  | Compile Master Note Doc thingy |  |  | Gather Gameplay Notes
| 2017-04-10 | Mon | BBL Dying from Flu |  | Updating Character Selection
| 2017-04-11 | Tue |  |  |  |  | Gotta Tone Down Light Juice
| 2017-04-12 | Wed | Taking Care of Trailer |  |  |  | Double Check with Staff About Beta Burndown Chart
| 2017-04-13 | Thu | Can't make Expo cause class | Can't Make Expo cause work | Talking to Brother to Get Audio for game and trailer. Going to Design Expo | Going To Design Expo
| 2017-04-14 | Fri
| 2017-04-15 | Sat |  | QA Testing |  | QA Testing
| 2017-04-16 | Sun |  |  |  |  | Make Sure Everything is Ready for Gamma Turn in
| 2017-04-17 | Mon |  |  |  | 441 Stuff =(
| 2017-04-18 | Tue |  |  |  |  | Bug Fixing From here on Out
| 2017-04-19 | Wed
| 2017-04-20 | Thu
| 2017-04-21 | Fri
| 2017-04-22 | Sat
| 2017-04-23 | Sun
| 2017-04-24 | Mon